## RACI Charts
Steps will be highlighted if A and R are not assigned.
[6 empty] | R: | Does the step
Responsibility Assignment Matrix | [5 empty] | A: | Accountable for the step
[6 empty] | C: | Consulted with before the step
[6 empty] | I: | Informed when the step is completed
| Project: |  | Systems Migration Project, J.D. Monster Bank
| STEP | PHASE | DESCRIPTION | VP Information Technology | Program Manager | Project Manager | Technical Manager | Project Coordinator | Network Support Lead | Programmers | Bank Representatives | Customer Engagement Strategist | Training Manager | IT Support Administrator | Infrastructure Provider Contractor | Database Analysts | Analysis Experts | Assistants | IT Assistants
| 1 | Project Initiation | Develop Requirement Document | I | A | R | R | C | I | I | I | I | I | I |  | I | I
| 2 | Project Initiation | Identify Stakeholders | I | R | R | A | C | I | I | I | I | I | I |  | I
| 3 | Project Initiation | Define Organizational Structure | I | R | R | A | C | I | I | I | I | I | I |  | I
| 4 | Project Initiation | Develop Project Charter | I | R | R | A | A | I | I | I | I | I | I |  | I |  |  | I
| 5 | Project Planning | Define Project Objectives And Milestones | I | R | R | C | A | I | I | I | I | I | I | I | I | I |  | I
| 6 | Project Planning | Develop Migration Plan | I: I; R: R; R: R; C: R; A: A; I: C; I: I; I: C
| 7 | Project Planning | Project Budgeting | A | R | R | C | C | I | C | I | I |  | I | I | I |  |  | I
| 8 | Project Planning | HR Planning | C | R | R | C | A |  |  | I | I | I | I | I | I | I | I | I
| 9 | Project Planning | Project Scheduling | C | C | R | C | A | I | I | I | I | I
| 10 | New Platform Preparation | Acquire And Review API | I | A | R | R | A |  | R | I | I | I | C | I | I | C | I | I
| 11 | New Platform Preparation | Review Billing Structures | C: C; C: A; R: R; C: C; A: C
| 12 | New Platform Preparation | Define Data Migration Rules | C | A | R | R | A | C | C | I | I | I | C |  | C | C
| 13 | New Platform Preparation | Systems Configuration | C | A | R | R | A | C | C |  |  |  | A
| 14 | New Platform Preparation | Test User Account Setup | I | I | A | A | A | A | I |  |  |  | R |  |  |  |  | R
| 15 | New Platform Preparation | Database Configuration | I | I | A | A | A | I | C |  |  |  | R | I | R | A | I | R
| 16 | Existing Platform | Data Structure Blueprint And Analysis | I | A | R | R | C | I | I | I | I | I |  |  | C
| 17 | Existing Platform | Data Cleaning And Analysis | I | A | C | R | C | I | C | I | I | I |  |  | C
| 18 | Existing Platform | Design Staging Areas | I | A | R | A | A | I | A | [5 empty] | R
| 19 | Existing Platform | Task Review And QA | R | A | R | A | C |  | R | I | I | I | I | I | I | I | I | I
| 20 | Existing Platform | Trial Data Exports | I | C | A | R | A | C | R | I | I |  | C
| 21 | Existing Platform | Production Data Exports | I | C | R | A | C | C | C |  |  |  |  | C
| 22 | Import Services Routines | Map Trial Data To API | C | A | A | R | C | C | C | I | I | I | C | I | C | I | I | C
| 23 | Import Services Routines | Build Routines | C: I; A: C; A: A; R: R; C: A; C: R
| 24 | Import Services Routines | Test Routines | I | C | A | R | A |  | R | I | I | I | I | I | I | I | I | I
| 25 | Import Services Routines | Confirm Data Compliance | I | A | R | A | A |  |  | I | I | I | I | I | I | I | I | I
| 26 | Data Import | Trial Import | C: I; A: A; A: R; R: R; C: A; C: R
| 27 | Data Import | Testing And QA | I | I | C | R | A |  | R | I | I | I | I | I | I | I | I | I
| 28 | Data Import | Test Results Review | C: I; A: R; A: R; R: R; C: A; C: I; C: A
| 29 | Data Import | Trial Import Interactions | I | I | C | R | A |  | R | I | I | I | C | I | I | I | I | C
| 30 | Data Import | Production Imports | C: I; A: I; A: C; R: R; C: A; C: R
| 31 | Data Import | QA Review | C: I; A: R; A: R; R: R; C: A; C: I; C: A
| 32 | System Cut Over | Error Tracing And Bug Fixing | I | I | A | A | A |  | R | I | I | I | I | I | I | I | I | I
| 33 | System Cut Over | Patch Maintenance And Scheduling | I | I | A | A | A | C | R | I | I | I | I | I | I | I | I | I
| 34 | System Cut Over | Documentation | A | A | R | C | C | C | C | I | I | I | I | I | C | C
| 35 | System Cut Over | Decommissioning Of Earlier Used Systems | I | A | A | R | A | C | A |  |  |  | C |  | C